# Meeting notes [Weekly Study Updates] [18 SEP 26]

## Batch II: Patient Inclusion

| Cluster | Follow-up | Dec–Jan | Jan–Feb | Feb–Mar | Mar–Apr | Apr–May | May–Jun | Jun–Jul | Jul–Aug | Aug–Sep | Sep-Oct |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Dibrugarh | All | 7 | 30 | 23 | 19 | 19 | 17 | 24 | 17 | 33 | 02* |
|  | QoL/Dis | NA | NA | 11 | 8 | 4 |  | 9 | 4 | 29 | 02* |
|  | ATLS | NA | 12 | 5 | 10 | 8 | 6 | 8 | 5 | 06 | 01* |
| Holy Family | All | 25 | 29 | 14 | 14 | 12 | 12 | 10 | 13 | 15 | 01* |
|  | QoL/Dis | NA | NA |  | 9 | 3 |  | 2 | 3 | 12 | 01* |
|  | ATLS | NA | 1 | 6 | 9 | 6 | 4 | 5 | 4 | 05 | 01 |
| KEM | All | 9* | 25 | 9 | 16 | 10 | 14 | 7 | 14 | 24 | -- |
|  | QoL/Dis | NA | NA | NA | — | 4 |  | 3 | 7 | 21 03 Deaths | -- |
|  | ATLS | NA | NA | 4 | 6 | 4 | 2 | 2 | 6 | 05 | -- |
| Dayanand | All | 28 | 31 | 15 | 13 | 14 | 13 | 10 | 19 | 16* | 01* |
|  | QoL/Dis | NA | NA | NA | 3 | 8 |  | 1 | 3 | 16* | 01* |
|  | ATLS | NA | NA | NA | 1 | 6 | 7 | 7 | 14 | 13* | 01 |
| Sion | All | 20 | 15 | 12 | 10 | 16 | 15 | 17 | 26 | 17 | 17th SEP NIGHT |
|  | QoL/Dis | NA | NA (night 19 Feb) | NA | NA | NA |  |  | 5 | 14* | -- |
|  | ATLS | NA | NA | NA | NA | NA | 2 | 2 | 10 | 08* | -- |
| Monthly average | All | 17.8 | 26 | 14.6 | 14.4 | 14.2 | 14.2 | 13.6 | 17.8 | 21 | -- |
|  | QoL/Dis | NA | NA | 5.5 | 5 | 4.75 | NA | 3.75 | 4.4 | 18.4 | -- |
|  | ATLS | NA | 6.5 | 5 | 6.5 | 5 | 4.2 | 4.8 | 7.8 | 7.4 | -- |

## [Batch II Data]

| Variables | AMC (N= 256) | Holy Family (N= 192) | Sion (N= 136) | DMC (N= 158) | KEM (N= 92) | Total (835) |
| --- | --- | --- | --- | --- | --- | --- |
| Total Injuries | 410 | 574 | 652 | 570 | 389 | 2595 |
| Age in years, median (IQR) | 40 (27 to 54) | 38 (27 to 52) | 32.5 (23 to 44.25) | 42 (28 to 56) | 33 (25 to 42) | 37 (26 to 52) |
| Missing no. (%) | 0(0) | 1 (0.5) | 7 (4.9) | 0 (0) | 1 (1.1) | 9 (1.2) |
| Female sex, no. (%) | 40 (15.6) | 62 (32.5) | 17 (12.5) | 23 (14.6) | 14 (15.1) | 156 (18.7) |
| Missing no. (%) | 0 (0) | 2 (1.0) | 7 (4.9) | 0 (0) | 0 (0) | 9 (1.2) |
| Mechanism of injury, no. (%) |  |  |  |  |  |  |
| Transport | 165 (64.5) | 96 (50.0) | 58 (42.6) | 133 (84.2) | 48 (52.2) | 500 (59.9) |
| Fall | 61 (23.8) | 51 (26.6) | 36 (26.5) | 18 (11.4) | 14 (15.2) | 180 (21.6) |
| Assault | 13 (5.1) | 9 (4.7) | 34 (25.0) | 6 (3.8) | 17 (18.5) | 79 (9.5) |
| Self-harm | 0 (0) | 23 (11.9) | 3 (2.2) | 0 (0) | 1 (1.1) | 27 (3.2) |
| Other | 16 (6.3) | 12 (4.7) | 6 (4.4) | 0 (0) | 11 (11.9) | 45 (5.4) |
| Missing (%) | 1 (0.4) | 0 (0) | 10 (7.4) | 0 (0) | 1 (1.1) | 14 (1.7) |
| Transfer, no. (%) | 153 (61.4) | 43 (23.8) | 88 (64.7) | 76 (48.1) | 37 (39.8) | 398 (48.7) |
| SBP, median (IQR)* | 110 (100 to 128) | 120 (110 to 140) | 114 (110 to 126) | 120 (110 to 140) | 120 (110 to 130) | 120 (110 to 130) |
| Missing, no. (%) | 19 (7.4) | 26 (13.5) | 11 (7.7) | 0 (0) | 11 (11.8) | 70 (8.3) |
| RR, median (IQR)* | 18 (17.5 to 20.5) | 20 (20 to 22) | 20 (18 to 20) | 20 (20 to 24) | 20 (20 to 22) | 20 (20 to 22) |
| Missing, no. (%) | 248 (96.9) | 26 (13.5) | 130 (90.9) | 23 (14.6) | 72 (77.4) | 503 (59.4) |
| SpO2, median (IQR)* | 98 (96 to 98) | 98 (97 to 99) | 98 (98 to 99) | 97 (95 to 98) | 98 (98 to 99) | 97 (98 to 99) |
| Missing, no. (%) | 13 (5.1) | 24 (12.4) | 14 (9.8) | 0 (0) | 10 (10.8) | 64 (7.6) |
| GCS, median (IQR)* | 15 (7 to 15) | 15 (15 to 15) | 15 (15 to 15) | 15 (13 to 15) | 15 (14 to 15) | 15 (12 to 15) |
| Missing, no. (%) | 13 (5.1) | 25 (13.0) | 11 (7.7) | 1 (0.6) | 15 (16.1) | 68 (8.0) |
| CT, no. (%) | 345 (55.1) | 208 (29.3) | 183 (38.4) | 176 (39.2) | 116 (30.8) | 1029 (38.9) |
| Surgery, no. (%) | 38 (17.0) | 250 (75.5) | 28 (20.9) | 83 (48.3) | 19 (20.2) | 418 (43.7) |
| ICU admission, no (%) | 107 (42.0) | 42 (25.3) | 112 (83.6) | 53 (35.9) | 30 (32.3) | 304 (39.8) |
| Hospital disposition, no. (%) |  |  |  |  |  |  |
| Alive | 152 (61.8) | 158 (89.8) | 109 (81.3) | 152 (96.2) | 64 (68.8) | 636 (78.7) |
| Dead | 94 (38.2) | 7 (4.0) | 25 (18.7) | 6 (3.8) | 29 (31.2) | 161 (19.9) |
| Transfer | 0 (0) | 11 (6.3) | 0 (0) | 0 (0) | 0 (0) | 11 (1.4) |
| Missing | 11 (4.3) | 11 (6.3) | 11 (7.6) | 1 (0.6) | 0 (0) | 34 (4.4) |

## 3. [Batch III Progress]

| Site / Centre | Update |
| --- | --- |
| PGI – Chandigarh | EC Approval received, working on Mandate for Agreement. |
| Kolkata Medical College | EC Approval received, CTA- Non-Financial to be executed with consultant agreement. |
| GMC Patiala | EC Approval received, Non-Financial CTA shared with addressed comments. |
| SMHS, Srinagar | EC Approval received, MOU Signed and couriered back to TGI. |
| MAMC, Delhi | Signed MOU - delivered MAMC, EC Queries & MOU Sent to research cell and legal team. |
| Doon Medical College | Departmental review completed – Expedited review requested, although EC Meeting is planned in 4th Week of SEP |
| SKIMS Soura | Submitted to EC; Meeting is planned in SEP |
| Safdarjung, Delhi | Reviewing CTA Comments and Departmental Submission. |
| Shija Hospitals and Research Institute, Imphal - Manipur | Screening Interview reflections: 1. Training medical officer 2. ATLS trained doctors (03/15) DNBs=6, EMO=7, SR=1, Consultant=1. Total=15. 3 out of 15 are certified (20%). |
| BRAIMS, Mohali | Screening Call Completed. |
| Overall: | 04 EC Approval’s- 01 Pending MAMC/Doon. 02 Agreements Executed (Including Srinagar, MAMC Half) - 03 Pending KMC/GMC/PGI/Doon. |

## 4. Decisions and actions

| Action | Owner | Due |
| --- | --- | --- |
| ATLS Training | PK-DB | Completed except KEM remaining candidates. 02 Candidates to be trained at LIHS, Mumbai 09-11 OCT. |
| KI-TGI Agreement | MW-AB | Latest progress to be discussed. |
| AIS Coding | MW | Mangled Hand AIS Code - |