General Updates: 9th OCT 2025

| Site Name | Total Screened | Total Enrolled | Total Consented | Data entry | Safety Event | ATLS Adherence |
| --- | --- | --- | --- | --- | --- | --- |
| Cooper | 1931 | 68 | 44 | 1754 | 00 | 12 |
| HIMS | 1364 | 169 | 96 | 1000 | 06 | 08 |
| SSKM | 862 | 374 | 383 | 437 | 10 | 61 |
| CMC | 156 | 74 | 61 | 152 | 03 | 50 |
| GMC | 179 | 180 | 136 | 110 | 01 | 29 |

Monthly Enrollment

| Cluster | Mar | Apr | May | Jun | Jul | AUG | SEP | OCT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cooper | 13 | 11 | 10 | 05 | 06 | 12 | 08 | 03* |
| HIMS | 20 | 27 | 29 | 26 | 21 | 28 | 12 | 06* |
| SSKM | 47 | 66 | 58 | 48 | 59 | 50 | 46 | 09* |
| GMC | 04 | 12 | 33 | 32 | 30 | 21 | 39 | 09* |
| CMC | 12 | 03 | 03 | 18 | 12 | 12 | 12 | 02* |

FEB: SSKM – 14 CMC – 02.

Monthly ATLS

| Cluster | Mar | Apr | May | Jun | Jul | AUG | SEP | OCT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CMC | NA | 02 | 03 | 14 | 11 | 12 | 08* = 50 | 01 |
| Cooper | NA | NA | 04 | 01 | 02 | 03 | 02* =12 | 01 |
| GMC | NA | NA | NA | 12 | 09 | 03 | 06* = 29 | 05 |
| SSKM | NA | NA | NA | NA | 18 | 19 | 24 = 61 | NA |
| HIMS | NA | NA | NA | NA | NA | 05 | 03* = 8 | 01 |

Other Updates:

- CMC ATLS Training in JULY:

- Centre: Adesh Medical College Ambala

- Training Date: 11 to 14 JULY

- Training Completed.

- Cooper ATLS Training in AUGUST:

  - Registration done for Centres: (5+5)

- Manipal Bangalore, 07 to 09 AUG- Training Completed.

- L.T.M. Medical College, Mumbai; Training Completed: 21 to 23 AUG.

- GMC Chandigarh- Arrangements completed for 4 centres- (3 Candidates/centre)

    - AAHL, Bengaluru (14-16 SEP) Training completed

    - KGMU Lucknow (18-20 SEP – Completed),

    - Sir Ganga Ram Hospital, New Delhi (24-26 SEP) –Completed.

    - IIEMS Cochin (25-27 SEP)- –Completed.

    - In Registration process:

- SSKM Kolkata-

- In process for Apollo Chennai – 16-18 OCT.

- Registration completed - KGMU, Lucknow 30th OCT 1st NOV.

- HIMS – NOV 2025: In process for centres:

- Sir Ganga Ram Hospital, New Delhi

19-21 NOV– 05 Candidates.

- MGUMST Jaipur -27-29 NOV 05 Candidates.

  - Batch II:

  - 1. Holy Family, Delhi - EC Approval received and CTA executed.

  - 2. KEM, Mumbai– EC Approval received, and CTA executed.

  - 3. Dayanand, Ludhiana – EC Approval received, and CTA executed.

  - 4. SION, Mumbai – EC Approval received, and CTA executed

  - 5. Assam Medical College, Dibrugarh – EC Approval received 8th OCT, and CTA execution ongoing.

  - Batch III:

1. PGI – Chandigarh –Final Comments!

  - 2. Kolkata Medical College – Screening details updated. Screening interview time to be confirmed.

      - 3. Kalpana Chawla Government Medical College & Hospital, HR– -     Scientific review process to be initiated.

4. Srinagar Government Medical College – Awaiting upcoming EC Date.

5. Pandit Bhagwat Dayal Sharma Post Graduate Institute of Medical Sciences, Rohtak – Non-Inclusion status updated.

Additional Points:

- Call with Copper regarding low recruitment conducted on 9th OCT

- Sara’s Internship

- Android Tablet procured to GMC CRC 9th OCT.