# ADVANCE TRAUMA

Trial Management Group

Meeting

May 11, 2026

- Members

Martin Gedin Wärnberg, Chair (MGW), present

Prashant Kharat (PK), present

Rajdeep Singh (RS), present

Kapil Dev Soni (KDS), present

Li Felländer-Tsai (LFT), present

Monty Khajanchi (MK), present

Johanna Berg (JB)

Anurag Mishra (AM)

Debojit Basak (DB)

Vivekanand Jha (VJ)

Girish Bakshi (GB)

Shamita Chatterjee (SC)

Abhinav Bassi (AB)

Karla Hemming (KH)

Anna Olofsson (AO)

Nobhojit Roy (NR)

Lovisa Strömmer (LS)

Agenda

- Batch 2 Patient inclusion update (Table 1, page 3)

- Batch 1 data review (Table 2, page 4)

- Batch 2 data review (Table 3, page 5)

- Batch 3 update

- Batch 2 ATLS training update

- Next meeting

- Any other business

Batch 2 patient inclusion update

Monthly inclusions are looking okay.

Batch 1 data review

Batch 2 data review

Batch 3 update

- PGI – Chandigarh – EC meeting conducted on 15 APR, EC queries received, will be submitting the response shortly.

- Kolkata Medical College – EC meeting rescheduled around 17 MAY.

- Kalpana Chawla Government Medical College & Hospital, HR– Scientific review process completed, EC Meeting date to be confirmed.

- GMC Patiala – EC Submission completed, Research Committee was scheduled, further update expected around 9th MAY. Agreement queries to be discussed today evening i.e. 7th MAY.

- Safdarjung - EC Submission in process (Dr Raj Kumar Chejara - PI)

- MOU/ Ethics Submission form.

- Srinagar Government Medical College – EC meeting conducted on 25th APR; EC approval and comments on agreement expected around 9th MAY.

Additional sites:

    - Additional sites:

    - MAMC – EC Submission Initiated.

    - SRMS, Bareilly - Screening call completed 19th FEB to be discussed (Majorly trained.)

    - AIIMS, Raebareli – Screening call completed.

    - Sir Gangaram Delhi – Scheduling Screening Interview.

    - KIMS hospital, Bengaluru- Contact established with Prof Madhushankar – will receive details of Emergency HOD.

Batch 2 ATLS training update

AMC Dibrugarh Training Schedule: (3+4 Candidates)

| Centre | Training Dates |
| --- | --- |
| Anand Abhigyan Healthcare and Life Sciences, Bangalore | 03–05 MAY 2026 Training Completed |
| Malla Reddy Institute, Hyderabad | 23-25 MAY 2026 |

Holy Family Training Schedule: (3+3+4 Candidates)

| Centre | Training Dates |
| --- | --- |
| TACT, Hyderabad | 23-25 MAY 2026 |
| LTM, Mumbai | 05–07 JUN 2026 |
| Malla Reddy Institute, Hyderabad | 12-14 JUN 2026 |

Next meeting

Any other business

| Table 1. Batch 2 patient inclusion |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Cluster | Cohort | Period 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 |  |
|  |  | 15th Dec to 15th Jan | 16th Jan to 15th Feb | 16th Feb to 15th Mar | 16th Mar to 15th April | 16th Apr to 15th May | 16th May to 15th Jun | 16th Jun to 15th Jul | 16th Jul to 15th Aug | 16th Aug to 15th Sep | 16th Sep to 15th Oct | 16th Oct to 15th Nov | 16th Nov to 15th Dec | 16th Dec to 15th Jan |  |
| Dibrugarh | All | 07 | 30 | 23* | 19* | 09* |  |  |  |  |  |  |  |  |  |
|  | QoL/Dis | NA | NA | 11 | 08* | 04 |  |  |  |  |  |  |  |  |  |
|  | ATLS | NA | 12 | 05 | 10* | 05* |  |  |  |  |  |  |  |  |  |
| Holy Family | All | 25 | 29 | 14 | 14* | 08* |  |  |  |  |  |  |  |  |  |
|  | QoL/Dis | NA | NA | ? | 09* | 03* |  |  |  |  |  |  |  |  |  |
|  | ATLS | NA | 01* | 06* | 09 | 02* |  |  |  |  |  |  |  |  |  |
| KEM | All | 09* | 25* | 09* | 16* | 09* |  |  |  |  |  |  |  |  |  |
|  | QoL/Dis | NA | NA | NA | -- | 04* |  |  |  |  |  |  |  |  |  |
|  | ATLS | NA | NA | 04* | 06* | 04* |  |  |  |  |  |  |  |  |  |
| Dayanand | All | 28 | 31 | 15* | 13* | 11* |  |  |  |  |  |  |  |  |  |
|  | QoL/Dis | NA | NA | NA | 03* | 08* |  |  |  |  |  |  |  |  |  |
|  | ATLS | NA | NA | NA | 01* | 06* |  |  |  |  |  |  |  |  |  |
| Sion | All | 20 | 15 | 12 | 10* | 06* |  |  |  |  |  |  |  |  |  |
|  | QoL/Dis | NA | NA | NA | NA | NA |  |  |  |  |  |  |  |  |  |
|  | ATLS | NA | NA | NA | NA | NA |  |  |  |  |  |  |  |  |  |

Note: Bold numbers indicate periods where the target of 12 participants have been met for that cluster and period. *Indicate that the numbers are not final and might be updated.

| Table 2. Batch 1 summary data |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Characteristic | Cooper (n = 138) |  | HIMS (n = 206) | SSKM (n = 682) | CMC (n = 100) | GMC (n = 226) | Overall (n = 1353) |
| Total Injuries | 454 |  | 536 | 2571 | 159 | 338 | 4171 |
| Age in years, median (IQR) | 32 (24-45) |  | 37 (26-54) | 39 (26-55) | 37 (26-50) | 35 (25- 47) | 37 (26 to 53) |
| Missing no. | 1 (0.7) |  | 3 (1.4) | NA | NA | NA | 3 (0.2) |
| Female sex, no. (%) | 19 (13.8) |  | 41 (19.9) | 121 (17.7) | 21 (21) | 29 (12.8) | 232 (17.1) |
| Missing no. | 1 (0.7) |  | 3 (1.4) | NA | NA | NA | 3 (0.2) |
| Mechanism of injury, no. (%) |  |  |  |  |  |  |  |
| Transport | 57 (48.7) |  | 97 (51.2) | 430 (66.1) | 54 (58.1) | 104 (59.1) | 742 (60.3) |
| Fall | 31 (26.5) |  | 70 (37.2) | 164 (25.2) | 14 (15.1) | 30 (17.1) | 309 (25.1) |
| Assault | 19 (16.2) |  | 6 (3.2) | 14 (2.2) | 12 (12.9) | 31 (17.6) | 82 (6.7) |
| Self-harm | 2 (1.6) |  | 11 (5.9) | 3 (0.5) | 2 (2.1) | 3 (1.7) | 21 (1.7) |
| Other | 3 (2.5) |  | 4 (2.1) | 39 (6.0) | 11 (11.8) | 5 (2.8) | 62 (5.0) |
| Missing | 5 (4.2) |  | 5 (2.5) | NA | NA | 3 (1.7) | 13 (1.1) |
| Transfer, no. (%) | 21 (15.6) |  | 67 (32.7) | 522 (76.5) | 23(23) | 187 (83.9) | 820 (61.0) |
| SBP, median (IQR)* | 110 (100-121) |  | 120 (110-140) | 127 (116-138) | 120 (100-140) | 125 (110-138) | 123 (110- 138) |
| Missing, no. | 5 (3.6) |  | 10 (4.8) | 51 (7.5) | 5 (5.3) | 6 (2.7) | 76 (5.6) |
| RR, median (IQR)* | 22 (19-24) |  | 19 (18-20) | 20 (18-21) | 20 (20-22) | 22 (20-24) | 20 (18 – 22) |
| Missing, no. (%) | 6 (4.3) |  | 8 (3.8) | 73 (10.7) | 18 (19.1) | 7 (3.1) | 111 (8.2) |
| SpO2, median (IQR)* | 98 (98-99) |  | 98 (96-99) | 99 (97-100) | 98 (97-100) | 96 (92-98) | 98 (96 – 99) |
| Missing, no. (%) | 5 (3.6) |  | 8 (3.8) | 19 (2.8) | 2 (2.1%) | 17 (7.5) | 50 (3.7) |
| GCS, median (IQR)* | 15 (12-15) |  | 15 (6-15) | 15 (13-15) | 15 (13-15) | 15 (15-15) | 15 (13 – 15) |
| Missing, no. (%) | 13 (9.4) |  | 4 (1.9) | 9 (1.3) | 2 (2.1%) | 14 (6.2) | 41 (3.0) |
| CT, no. (%) | 105 (32.7) |  | 384 (31.9) | 713 (30.4) | 87 (46.5) | 275 (37.0) | 1564 (32.6) |
| Surgery, no. (%) | 26 (20.8) |  | 73 (34.3) | 378 (52.3) | 27 (26.7) | 72 (32.3) | 582 (41.2) |
| ICU admission, no (%) | 94 (89.5) | 18 (17.3) |  | 289 (42.4) | 21 (24.7) | 7 (3.2) | 429 (36.0) |
| Hospital disposition, no. (%) |  |  |  |  |  |  |  |
| Alive | 121 (89.6) | 184 (89.8) |  | 462 (72.9) | 97 (97) | 208 (95.4) | 1107 (83.2) |
| Dead | 13 (9.6) | 21 (10.2) |  | 150 (23.7) | 3 (3) | 5 (2.3) | 193 (14.5) |
| Transfer | 1 (0.7) | NA |  | 22 (3.5) | NA | 3 (1.4) | 28 (2.1) |
| Missing | NA | NA |  | NA | NA | 2 (0.9) | 2 (0.2) |

| Table 3. Batch 2 summary data |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Characteristic | AMC (n = 75) |  | Holy Family (n = 94) | Sion (n = 32) | DMC (n = 98) | KEM (n = 43) | Total (n = 331) |
| Total Injuries | 119 |  | 107 | 82 | 326 | 56 | 716 |
| Age in years, median (IQR) | 39 (27 to 54) |  | 37 (26 to 51) | 32 (26 to 47) | 42 (23 to 56) | 33 (25 to 45) | 38 (27 to 52) |
| Missing no. | 0 (0) |  | 3 (3.1) | 0 (0) | 0 (0) | 1 (2.3) | 3 (3.1) |
| Female sex, no. (%) | 14 (18.2) |  | 35 (37.2) | 2 (6.3) | 11 (11.2) | 7 (16.3) | 64 (19.3) |
| Missing no. | 0 (0) |  | 3 (3.1) | 0 (0) | 0 (0) | 0 (0) | 3 (3.1) |
| Mechanism of injury, no. (%) |  |  |  |  |  |  |  |
| Transport | 44 (58.7) |  | 45 (47.8) | 13 (40.6) | 80 (81.6) | 20 (46.5) | 195 (58.9) |
| Fall | 17 (22.7) |  | 29 (30.9) | 7 (21.8) | 14 (14.3) | 5 (11.6) | 74 (22.4) |
| Assault | 5 (6.7) |  | 2 (2.1) | 8 (25.0) | 2 (2.0) | 9 (20.9) | 25 (7.6) |
| Self-harm | 0 (0) |  | 9 (9.6) | 1 (3.0) | 0 (0) | 0 (0) | 11 (3.3) |
| Other | 8 (10.7) |  | 9 (9.6) | 3 (9.3) | 0 (0) | 9 (20.9) | 23 (6.7) |
| Missing | 1 (1.3) |  | 0 (0) | 0(0) | 2 (2.0) | 0 (0) | 3(3.1) |
| Transfer, no. (%) | NIL |  | 11 (14.9) | 16 (50) | 44 (44.9) | 1 (2.3) | 87 (26.3) |
| SBP, median (IQR)* | 110 (101 to 120) |  | 120 (110 to 140) | 120 (110 to 130) | 130 (110 to 140) | 120 (110 to 122) | 120 (110 to 130) |
| Missing, no. | 3 (3.9) |  | 21 (21.6) | 0 (0) | 0 (0) | 0 (0) | 24 (7.3) |
| RR, median (IQR)* | 18 (17 to 19) |  | 20 (20 to 22) | 20 (18 to 20) | 20 (20 to 24) | 20 (20 to 20) | 20 (20 to 22) |
| Missing, no. (%) | 70 (90.9) |  | 21 (21.6) | 19 (59.4) | 14 (14.3) | 24 (55.4) | 143 (43.2) |
| SpO2, median (IQR)* | 98 (97 to 98) |  | 98 (97 to 99) | 98 (98 to 99) | 97 (95 to 98) | 98 (98 to 99) | 98 (96 to 99) |
| Missing, no. (%) | 2 (2.6) |  | 21 (21.6) | 1 (3.1) | 0 (0) | 1 (2.3) | 25 (7.6) |
| GCS, median (IQR)* | 15 (15 to 15) |  | 15 (15 to 15) | 15 (15 to 15) | 15 (14 to 15) | 15 (15 to 15) | 15 (15 to 15) |
| Missing, no. (%) | 2 (2.6) |  | 22 (22.7) | 2 (6.3) | 1 (1.0) | 3 (7.0) | 29 (8.8) |
| CT, no. (%) | 135 (43.3) |  | 44 (27.7) | 30 (65.2) | 86 (36.4) | 28 (62.2) | 325 (40.3) |
| Surgery, no. (%) | 3 (10.0) |  | 44 (77.2) | 4 (12.5) | 57 (55.3) | 4 (9.8) | 112 (42.1) |
| ICU admission, no (%) | Nil | 7 (16.3) |  | 23 (71.9) | 10 (13.0) | 13 (30.2) | 63 (19.0) |
| Hospital disposition, no. (%) |  |  |  |  |  |  |  |
| Alive | 70 (95.9) | 44 (97.8) |  | 28 (87.5) | 94 (95.9) | 41 (95.3) | 268 (80.9) |
| Dead | 3 (4.1) | 0 (0) |  | 4 (12.5) | 4 (4.1) | 2 (4.7) | 15 (4.5) |
| Transfer | 0 (0) | 1 (2.2) |  | 0 (0) | 0 (0) | 0 (0) | 1 (0.3) |
| Missing | 2 (2.6) | 43 (48.9) |  | 0 (0) | 0 (0) | 0 (0) | 45 (13.6) |