- Batch 2 Patient Inclusion:

| Cluster | Follow up | 15th Dec to 15th Jan | 16th Jan to 15th Feb | 16th Feb to 15th March | 16th March to 15th April | 16th April to 15th May | 16th May to 15th June | 16th June to 15th July | 16th July to 15th August | 16th AUG to 15th SEP |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Dibrugarh | All | 7 | 30 | 23 | 19 | 19 | 17 | 24 | 17 | 06* |
|  | QoL/Dis | NA | NA | 11 | 8 | 4 |  | 9 | 04 | 02* |
|  | ATLS | NA | 12 | 5 | 10 | 8 | 06 | 8 | 05 | 02* |
| Holy Family | All | 25 | 29 | 14 | 14 | 12 | 12 | 10 | 13 | 02* |
|  | QoL/Dis | NA | NA |  | 9 | 3 |  | 02 | 03 | -- |
|  | ATLS | NA | 1 | 6 | 9 | 6 | 04 | 05 | 04 | 01* |
| KEM | All | 09* | 25 | 9 | 16 | 10 | 14 | 07 | 14 | 03* |
|  | QoL/Dis | NA | NA | NA | -- | 4 |  | 3 | 07 | 03* |
|  | ATLS | NA | NA | 4 | 6 | 4 | 02 | 2 | 06 | -- |
| Dayanand | All | 28 | 31 | 15 | 13 | 14 | 13 | 10 | 19 | 02* |
|  | QoL/Dis | NA | NA | NA | 3 | 8 |  | 01 | 03 | 01* |
|  | ATLS | NA | NA | NA | 1 | 6 | 07 | 07 | 14 | 01* |
| SION | All | 20 | 15 | 12 | 10 | 16 | 15 | 17 | 26 | Today’s NIGHT |
|  | QoL/Dis | NA | NA (Night 19th FEB) | NA | NA | NA |  |  | 05 | -- |
|  | ATLS | NA | NA | NA | NA | NA | 02 | 02 | 10 | -- |
| Monthly Average | All | 17.8 | 26 | 14.6 | 14.4 | 14.2 | 14.2 | 13.6 | 17.8 | 3.2 |
|  | QoL/Dis | NA | NA | 5.5 | 5 | 4.75 | NA | 3.75 | 4.4 | 2 |
|  | ATLS | NA | 6.5 | 5 | 6.5 | 5 | 4.2 | 4.8 | 7.8 | 1.3 |

- Batch 2 Data:

| Variables | AMC (N= 240) |  | Holy Family (N= 170) | Sion (N= 124) | DMC (N= 144) | KEM (N= 85) | Total (763) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Total Injuries | 358 |  | 367 | 516 | 486 | 355 | 2082 |
| Age in years, median (IQR) | 41 (28 to 54) |  | 36 (26 to 51) | 33 (23 to 44) | 42 (28 to 57) | 35 (25 to 45) | 38 (26 to 52) |
| Missing no. (%) | 0(0) |  | 1 (0.6) | 7 (5.3) | 0 (0) | 1 (1.2) | 9 (1.2) |
| Female sex, no. (%) | 35 (14.6) |  | 58 (34.3) | 15 (12.1) | 21 (14.6) | 13 (15.5) | 143 (18.7) |
| Missing no. (%) | 0 (0) |  | 2 (1.2) | 7 (5.3) | 0 (0) | 0 (0) | 9 (1.2) |
| Mechanism of injury, no. (%) |  |  |  |  |  |  |  |
| Transport | 151 (65.1) |  | 76 (47.2) | 45 (39.5) | 115 (83.9) | 51 (61.4) | 438 (60.2) |
| Fall | 55 (23.7) |  | 44 (27.3) | 33 (28.9) | 17 (12.4) | 11 (13.3) | 160 (22.0) |
| Assault | 10 (4.3) |  | 7 (4.3) | 28 (24.6) | 4 (2.9) | 16 (19.3) | 65 (8.9) |
| Self-harm | 0 (0) |  | 21 (13.0) | 3 (2.6) | 1 (0.7) | 1 (1.2) | 26 (3.5) |
| Other | 15 (6.4) |  | 13 (8.0) | 5 (4.4) | 0 (0) | 12 (14.4) | 45 (6.2) |
| Missing (%) | 1 (0.4) |  | 0 (0) | 0 (0) | 0 (0) | 0 (0) | 1 (0.8) |
| Transfer, no. (%) | 138 (59.2) |  | 33 (21.3) | 82 (66.1) | 68 (47.2) | 30 (35.7) | 353 (47.6) |
| SBP, median (IQR)* | 110 (100 to 128) |  | 120 (110 to 140) | 114 (110 to 126) | 120 (107 to 140) | 120 (110 to 130) | 120 (110 to 130) |
| Missing, no. (%) | 19 (7.9) |  | 29 (17.0) | 10 (7.6) | 0 (0) | 10 (11.9) | 68 (8.8) |
| RR, median (IQR)* | 18 (17 to 20) |  | 20 (20 to 22) | 20 (18 to 20) | 20 (20 to 24) | 20 (20 to 22) | 20 (20 to 22) |
| Missing, no. (%) | 232 (96.7) |  | 30 (17.5) | 118 (90.1) | 19 (13.2) | 63 (75.0) | 464 (60.1) |
| SpO2, median (IQR)* | 98 (96 to 98) |  | 98 (97 to 99) | 98 (98 to 99) | 97 (95 to 98) | 98 (98 to 99) | 98 (96 to 99) |
| Missing, no. (%) | 13 (5.4) |  | 28 (16.4) | 12 (9.2) | 0 (0) | 9 (10.7) | 62 (8.0) |
| GCS, median (IQR)* | 15 (7 to 15) |  | 15 (15 to 15) | 15 (15 to 15) | 15 (13 to 15) | 15 (14 to 15) | 15 (12 to 15) |
| Missing, no. (%) | 13 (5.4) |  | 30 (17.5) | 10 (7.6) | 1 (0.7) | 10 (11.9) | 65 (8.4) |
| CT, no. (%) | 329 (55.3) |  | 128 (26.2) | 167 (39.7) | 157 (39.0) | 105 (33.0) | 889 (39.7) |
| Surgery, no. (%) | 35 (17.0) |  | 155 (71.8) | 26 (21.7) | 76 (48.7) | 16 (19.0) | 308 (39.3) |
| ICU admission, no (%) | 101 (42.4) | 29 (23.6) |  | 102 (83.6) | 38 (26.6) | 29 (34.5) | 271 (40.1) |
| Hospital disposition, no. (%) |  |  |  |  |  |  |  |
| Alive | 142 (62.0) | 111 (87.4) |  | 97 (80.8) | 138 (95.8) | 55 (66.3) | 544 (77.2) |
| Dead | 87 (38.0) | 6 (4.7) |  | 23 (19.2) | 6 (4.2) | 28 (33.7) | 151 (21.4) |
| Transfer | 0 (0) | 10 (7.9) |  | 0 (0) | 0 (0) | 0 (0) | 10 (1.4) |
| Missing | 10 (4.2) | 29 (18.6) |  | 13 (9.8) | 1 (0.7) | 1 (1.2) | 54 (7.1) |

- Batch 3 Progress:

  - PGI – Chandigarh – EC meeting conducted on 15 APR -13th AUG ICRC Meeting conducted- Collaboration Letter requested– EC approval and CTA details will be received by 1-2 days.

  - Kolkata Medical College – EC meeting conducted 23 MAY, Approval received,

CTA agreed, shared for final legal review by 15th AUG, Agreement go ahead in 2-3 days.

  - GMC Patiala – EC Submission completed, EC Meeting scheduled on 21st May Agreement queries discussed. Approval received, agreement finalization-Account details received, SPOT Draft e-signing completed for TGI, PI – Comments from Dean, discussion initiated.

  - Srinagar Government Medical College – EC meeting conducted on 25th APR; EC approval received, Dr Arshad will rejoin by 16th AUG – Dean is not ready – Registrar/ Medical Superintendent contacted, shorter version proposed again to Dean on 18th AUG by 24th AUG we can expect the response.

  - MAMC Delhi – MOU to be executed by MON/TUE – 19 AUG – Signature from TGI completed and delivered MAMC, EC procedures to be initiated for waiver.

  - Safdarjung - EC Submission in process (Dr Raj Kumar Chejara - PI)

MOU/ Ethics Submission form; (Dr Anil Kumar awaiting confirmation from Dr Chejara)

  - Doon Medical College, EC Submitted- Departmental review – 3rd week of AUG, if passed try expedited review.

  - CRCs finalized.

03 EC Approvals in hand, PGI Next Week + MAMC Waiver

CTAs: GMC Patiala Signing, Targetting – Kolkata Medical College+ PGI+MAMC+ Srinagar

Additional sites that are being followed:

- Hindu Mission Hospital, Chennai.

- Believers Church Medical College Hospital, Kerala

- GMC Amritsar

- Imphal, Manipur.

AMC Dibrugarh Training Schedule: (3+4 Candidates)

| Centre | Training Dates |
| --- | --- |
| Anand Abhigyan Healthcare and Life Sciences, Bangalore | 03–05 MAY 2026 *Training Completed All 3 Passed. |
| TACT, Hyderabad | 23-25 MAY 2026 |

Total 07 Candidates trained + 1 scheduled for 25-27 JUL-HYD

Holy Family Training Schedule: (3+3+4 Candidates)

| Centre | Training Dates |
| --- | --- |
| TACT, Hyderabad | 23-25 MAY 2026 |
| LTM, Mumbai | 05–07 JUN 2026 |
| Malla Reddy Institute, Hyderabad | 12-14 JUN 2026 |

*NEXT IN LINE – KEM – MUMBAI. – 29-31 OCT Training is available in MGM Mumbai.

(2+2+3)

| Centre | Training Dates |
| --- | --- |
| Anand Abhiyan Bengaluru – 02 Candidates | 05–07 July 2026 |
| TACT Hyderabad - 02 Candidates suggested | 25–27 July 2026 |
| TACT Chennai - 03 Candidates suggested | 13–15 August 2026 |

+ OCT Trainings to be targeted. MGM Mumbai offering 29-31 OCT*

*NEXT IN LINE – Dayanand –

| Centre | Training Dates |
| --- | --- |
| Anand Abhiyan Bengaluru – 02 Candidates | 05–07 July 2026 |
| TACT Hyderabad - 04 Candidates | 25–27 July 2026 |
| TACT Chennai - 04 Candidates | 13–15 August 2026 |
| TACT Hyderabad - 01 Candidates | 29–31 August 2026 |

NEXT IN LINE – SION* Froze 08 seats- Mumbai Centers: 04LIHS - AUG7-9 & 04MGM 20-22 AUG.