## ATLS Project Activity Plan
S. No. | Task Type | Steps/Milestones | Timeline | Responsibility
1 | Research | Protocol | Dec, 23 - Jan, 24 | KI
2 | Research | Protocol Synopsis | Dec, 23 - Jan, 24 | KI
3 | Operations | Trial Management Chart | Dec, 23 - Jan, 24 | TGI/KI
4 | Operations | Grant Agreement | Jan - Mar, 24 | TGI/KI
5 | Operations | Budget | Jan - Mar, 24 | TGI/KI
6 | Operations | TGI Staff Recruitment | Dec, 23 - Mar, 24 | TGI
7 | Operations | Laptop and Mobile Tablets Purchase | Dec, 23 - Mar, 24 | TGI
8 | Operations | TMF Index and TMF Setup | Dec, 23 - Mar, 24 | TGI
9 | Operations | ISF Index and ISF Setup | Dec, 23 - Mar, 24 | TGI
10 | Operations | Participant Documents Checklist | Dec, 23 - Mar, 24 | TGI
11 | Operations | Study Email-Id | Dec, 23 - Mar, 24 | TGI
12 | Operations | Study Template Development (Note to File, Delegation Log, Training Log, Site Activation Form, Database User Activation Form, and Site Closure Form, and Site Closure Checklist) | Dec, 23 - Mar, 24 | TGI
13 | Operations | Monitoring Visit Report Template (including Remote Monitoring Visit Report and Visit Letters) | Mar, 24 | TGI
14 | Operations | Trial Steering Committee Charter and Constitution | Jan, 23 - Mar, 24 | TGI/KI
15 | Operations | Data Safety and Monitoring Committee Charter and Constitution | Jan, 23 - Mar, 24 | TGI/KI
16 | Ethics and Regulatory | PIS/ICF Development | Jan - Feb, 24 | TGI/KI
17 | Operations | License for copyrighted tools and their translations | Jan - Feb, 24 | TGI/KI
18 | Ethics and Regulatory | CRF/Questionnaire | Jan - Feb, 24 | KI
19 | Database and data management | Data Dictionaries for EDC (Including, CRF, Logs for Screening and Enrolment, Protocol Deviation, and AE/SAE) | Jan - Feb, 24 | KI
20 | Database and data management | Randomisation Module | Feb, 24 | TGI
21 | Database and data management | Database Development and Randomisation Module Setup | Feb, 24 | TGI
22 | Database and data management | Database User Acceptability Testing | Mar - Apr, 24 | TGI
23 | Database and data management | Database Pilot Testing and Data Validation Report | May - Jun, 24 | TGI
24 | Database and data management | Reports/Dashboard Development | Apr - Jun, 24 | TGI
25 | Database and data management | Training Database Access to Sites | Jun, 24 | TGI
26 | Ethics and Regulatory | Intervention Details (Training Brochure) | Jan - Feb, 24 | TGI/KI
27 | Ethics and Regulatory | TGI-IEC Application Submission and Approval | Feb - Mar, 24 | TGI
28 | Operations | Site Confidentiality Agreements | Feb - Mar, 24 | TGI/KI
29 | Operations | Site Feasibility Assessment | Feb - Mar, 24 | TGI/KI
30 | Operations | Site Feasibility Report and Selection | Mar - Apr, 24 | TGI/KI
31 | Ethics and Regulatory | CTRI registration | Feb - Mar, 24 | TGI
32 | Ethics and Regulatory | Data Sharing Agreement for HMSC Application | Mar - June, 24 | TGI
33 | Ethics and Regulatory | HMSC Application | Mar - June, 24 | TGI
34 | Site Ethics | PIS/ICF Translations & Certificates | Mar - Apr, 24 | TGI/KI
35 | Operations | CTA Draft | Mar - Apr, 24 | TGI
36 | Operations | Insurance certificate | Mar - Apr, 24 | TGI
37 | Site Ethics | Site Ethics Submission and Approvals (Batch 1) | Apr - Jun, 24 | TGI
38 | Site Ethics | Clinical Trial Agreement (Batch 1) | Apr - Jun, 24 | TGI
39 | Site Operations | Site Staff Recruitment | Apr - Jun, 24 | TGI
40 | Database and data management | Database User Activation Form | Jun - Jul, 24 | TGI
41 | Database and data management | Electronic screening and enrolment, protocol deviation, treatment adherence, SAE | Feb, 24 | TGI/KI
42 | Operations | Trial Management Plan (including Trial Monitoring, Safety Reporting, Quality Assurance, Risk Management, and Filing and Archival) | Feb - May, 24 | TGI
43 | Database and data management | Data Monitoring Plan (Source Data Verification and Review, Safety Review, Outcomes Assessment) | Feb - May, 24 | TGI
44 | Operations | Manual of Operations for Sites | Feb - May, 24 | TGI
45 | Database and data management | Data Entry Manual/Videos | Feb - May, 24 | TGI
46 | Site Operations | Study Presentation Slide for Investigators Meeting and Site Initiation Visits | Feb - May, 24 | TGI/KI
47 | Site Operations | Site Team CV's | Apr - June, 24 | TGI/Sites
48 | Site Operations | Site GCP Trainings | Apr - June, 24 | TGI/Sites
49 | Site Operations | Site Team GCP Certificates | Apr - June, 24 | TGI/Sites
50 | Operations | DSMB Report Template
51 | Site Operations | Laboratory Reference Ranges | Apr - June, 24 | TGI/Sites
52 | Site Operations | Site Training | Jun - Jul, 24 | TGI/KI
53 | Site Operations | Site Training Log | Jun - Jul, 24 | TGI
54 | Site Operations | Site Delegation Log | Jun - Jul, 24 | TGI
55 | Site Operations | Site Training Certificate | Jun - Jul, 24 | TGI/KI
56 | Site Operations | Site Activation Checklist | Jul - Aug, 24 | TGI
57 | Site Operations | Site Activation Form | Jul - Aug, 24 | TGI
58 | Site Operations | First Site Initiation Visit | Jul - Aug, 24 | TGI
59 | Site Operations | Site Initiation Visit (SIV) Report | Aug, 24 | TGI
60 | Site Operations | First Site Activation | Jul - Aug, 24 | TGI
61 | Site Operations | First Participant Recruitment | Jul - Aug, 24 | TGI
62 | Site Operations | First Participant Recruitment Notification | Jul - Aug, 24 | TGI
63 | Site Operations | Remote Monitoring | Ongoing | TGI
64 | Database and data management | Safety Listing/Reports | Ongoing | TGI
65 | Trial Operations | Protocol Deviation/Protocol Violation Listing/Report | Ongoing
66 | Trial Operations | Interim Monitoring Visit | Ongoing | TGI/Sites
67 | Trial Operations | Interim Monitoring Visit Report | Ongoing | TGI/Sites
68 | Operations | Interim Report for DSMC | TBD | TGI
69 | Operations | DSMC Recommendations | TBD | TGI
70 | Operations | TSC Meetings | TBD | TGI/KI
71 | Operations | Audits | TBD | TGI/KI
72 | Operations | Study Newsletter | Half Yearly | TGI
73 | Operations | Annual Progress Report | Yearly | TGI/KI
74 | Operations | Database Cleaning | Ongoing | TGI
75 | Operations | Interim Database Lock | TBD | TGI
76 | Operations | Database Lock | TBD | TGI
77 | Site Operations | Site Closure Report | TBD | TGI/Sites
78 | Site Operations | Study Closure Report | TBD | TGI
79 | Statistics | Interim analysis report | TBD | TGI
80 | Statistics | Statistical Analysis Plan | End of Study | KI
81 | Statistics | Statistical Analysis Plan (SAP) Publication | TBD | KI
82 | Research | Protocol Paper Publication | TBD | KI
83 | Research | Journal Selection | TBD | KI
84 | Research | Results Publication/Commentary | TBD | KI
85 | Research | Author Confidentiality Forms | TBD | KI
86 | Research | Author Declarations | TBD | KI
87 | Research | Conflict of Interest Forms | TBD | KI