ATLS® vs standard care trial

Meeting with TGI to discuss project activity plan, 2023-12-20

# Agenda

* Research collaboration agreement
* Final budget
* Cluster screening
* Project activity plan

# Notes

* The research collaboration agreement is still being drafted by the KI legal team. Martin has reminded them. Will send to TGI as soon as a draft is ready.
* The agreement will mention the grant amount.
* The cluster screening is ongoing and hopefully there will be five hospitals shortlisted to be included in the first batch of hospitals by Friday December 22.
* We will need some ethical approvals to start the HMSC submission, and we will need the HMSC approval to get ethical approval, so it’s a bit of a catch 22. However, we should be able to get ethical approvals that are conditional on the HMSC approval, which is why it’s important to come up with a first batch of hospitals so that we can start the ethics process with them.
* We reviewed and discussed the project activity plan prepared by Samriddhi and Abhinav.
* TGI will be able to start working on the different elements in the project activity plan before the money is transferred, as long as there is a continuous exchange of documents between the parties and reviews of the research collaboration agreement.

# Decisions

* Martin will share PIS and ICF from a previous project.
* Martin will draft a CRF including the different components mentioned in the project activity plan.
* Samriddhi will share the project activity plan as well as some other relevant documents mentioned in that plan.
* We will meet again on December 10 at 11 CEST.