ATLS® vs standard care trial

Meeting with TGI, 2024-01-16

# Agenda

1. Activity plan review and progress
   1. How do we keep track of the progress, i.e. what is started/ongoing and how do we set deadlines within the longer timeline?
2. Expectations
   1. What are the expectations of all parties with regards to reviews, feedback and input?
3. Procedures
   1. Where do we store joint documents so that the latest versions are available to all?
4. Research collaboration agreement
5. Cluster screening
   1. Setting up screening interviews with individual hospitals
      1. H.B.T. Medical College & Dr. R.N. Cooper Municipal General Hospital, Mumbai
      2. All India Institute of Medical Sciences, Mangalagiri
      3. Christian Medical College and Hospital Ludhiana
      4. Rajawadi Hospital, Mumbai
      5. Government Medical College & Hospital, Chandigarh
      6. Himalayan Institute of Medical Sciences, Uttarakhand
6. Randomization
7. Other points

# Notes and decisions

1. TGI will create a Teams channel.
2. When we send an email with a draft document, we should also ask for feedback with a specific due date.
3. We will use the Teams channel and TGI will set up a shared drive.
4. Under review. First draft sent by Martin to TGI.
5. Martin will set up a cluster screening interview form that will include questions that TGI typically include in their site feasibility assessment. Monty will reach out to the sites that he has screened to set up calls with them. Martin will share the cluster screening interview form.
6. Not discussed.
7. Other points:
   1. The deadline for the TGI ethics committee meeting is February 7. Until then the protocol, CRF, patient information sheet and informed consent document need to be ready. To move things ahead we need to start applying for ethical permission, and need at least one to be able to register the trial with CTRI and to apply for HMSC approval. We should focus on finalise the five hospitals to be included in the first batch before HMSC approval.